| Date of Submission | September 2018 |
| --- | --- |

IPL Project Proposal Form 2018

(MAXIMUM: 3 PAGES IN LENGTH)

- Project Title: (2 lines maximum): Archival Records and Documentation of Some Socio-economically Significant Landslides in India

- Main Project Fields

Select the suitable topics. If no suitable one, you may add new field.

(1) Technology Development

A. Monitoring and Early Warning, B. Hazard Mapping, Vulnerability and Risk Assessment

(2) Targeted Landslides: Events, Impacts, Actions / Inactions and Lessons Learnt

A. Catastrophic Landslides, B. Landslides Threatening Heritage Sites

(3) Capacity Building

A. Enhancing Human and Institutional Capacities

B. Collating and Disseminating Information/ Knowledge

(4) Mitigation, Preparedness and Recovery

A. Preparedness, B. Mitigation, C. Recovery

- Name of Project leader: Dr. Surya Parkash

Affiliation (office and position): Head, Geo-meteorological Risks Management Division, National Institute of Disaster Management, Ministry of Home Affairs, Govt. of India, New Delhi

Contact (postal address, fax, phone, email): A-Wing, 4th Floor, NDCC-II Building, Jai Singh Road, New Delhi – 110001, INDIA, Phone:+91-11-23438293, Email: surya.nidm@nic.in, suryanidm@gmail.com

Likely Partners / Collaborators: Disaster Management Authorities at national, state & district levels

- Objectives: (5 lines maximum; what you expect to accomplish?)

- To collect and compile database on significant landslides in India

- To study and document important relevant information on socio-economically significant landslides from the archival records

- To prepare and develop brief case studies on some selected events, impacts, actions / inactions, and Lessons Learnt from these landslides

- To publish the outcomes of the study and use it as a knowledge resource for capacity enhancement on landslides risk reduction and resilience

- Background Justification (10 lines maximum):

Landslides in India are a common, wide spread, frequent and often sudden disasters in the hilly terrains, particularly adversely affecting the highways, human habitats, infrastructures, economy and environment. Due to the rapid pace of development, urbanization and changing climatic conditions, the trend in terms of both the occurrence of socio-economically significant landslides and their impacts seem to be rising. In the absence of adequate database and documentation of such landslides, it is difficult to assess the prevailing situations properly and plan proactively for efficient landslides risk reduction and resilience. There is an urgent dire need to document the past significant landslides along with lessons learnt (human memories are generally weak and the incidents are forgotten quickly with lapse of time if not well recorded).

Keeping in mind the above background, the project has been proposed to gather and study the archival records of the socio-economically significant landslides and document the events, impacts, actions take or not taken, and lessons learnt for finding our way ahead for reducing the landslides risks and strengthening the resilience in landslide prone areas.

- Study Area (2 lines maximum; where will the project be conducted/applied?): The project will be implemented at the national level in India.

- Project Duration: (1 line maximum): 3 years

- Resources necessary for the Project and their mobilization

Personnel: 2 (1 Young Professional for technical and field works and the 1 Young Professional for the IT and Database Management related to the project would be required).

Facilities: The Institute has adequate facilities for carrying out the proposed study.

Budget: 72000USD (The project may be financially supported by NIDM and ICL)

- Project Description (30 lines maximum): The project would require extensive study of the news articles, reports, websites, available publications, government memorandums, departmental investigations, social surveys and public interactions in the landslide affected areas of the country. A systematically designed structured format for collecting the database on landslide events, impacts, actions / inactions and lessons learnt would be developed for carrying out this study (The project would also consider the format suggested in World Report on Landslides but also examine the needs of disaster management authorities).

After collection and compilation of landslides database, analysis of the information will be done to summarize the outcomes of the study in a comprehensive manner to find out the trends and distributions of landslide events and their impacts as well as enhancing understanding about landslides, for disseminating the same to the concerned stakeholders for enhancing their human capacities for landslides risk reduction and resilience. Technical guidance and support from the expert members of ICL would be sought to make the study effective, practical and usable by the various stakeholders. Finally a publication would be brought out for wider sharing of this work in humanitarian interest at global level.

- Work Plan/Expected Results (20 lines maximum; work phases and milestones):

1 Year – Literature survey and studies including correspondence with concerned departments, news agencies, respective ministry and organizations / institutes etc.

6 months – Analysis of the available data and information as per requirements of the proposed study

1 Year – Documentation / Development of some selected case studies on significant landslides

6 months – Report writing and publication for dissemination of the acquired knowledge

- Deliverables/Time Frame (10 lines maximum; what and when will you produce?):

Database on Socio-economically Landslides in India – 1 year after the approval of project

Data Analysis and Brief Documentation of Some Selected Socio-economically Significant Landslides – 2 years 6 months after the approval of project

Publication of Final Report – 3rd year / Final year of the project

- Project Beneficiaries (5 lines maximum; who directly benefits from the work?):

The beneficiaries from the outcome of the project would include disaster management authorities at different levels (local, district, state and national), respective line departments and organizations, educational, research and training institutes working on landslides, affected communities, professionals engaged in developmental activities in such landslide affected areas.

- References (Optional) (6 lines maximum; i.e. relevant publications)

Parkash Surya, 2015: “Some Socio-Economically Significant Landslides in Uttarakhand Himalaya: Events, Consequences and Lessons Learnt”, Chapter 12 published in Mountain Hazards and Disaster Risk Reduction (eds.: Rajib Shaw and Hari Krishna Nibanupudi), Series on Disaster Risk Reduction – Methods, Approaches and Practices, published by Springer Japan, 2015, ISBN 978-4-431-55241-3, ISBN 978-4-431-55242-0(eBook), pp.211-232

Parkash Surya, 2015: “Tools, Techniques and Technologies for Capacity Enhancement to Reduce Landslide Risks and Promote Community Resilience”, Proceedings of International Conference on Landslides and Slope Stability (SLOPE 2015) – Advancement of Research, Practice and Integrated Solutions on Landslides, held at Bali, Indonesia during 27-30 September 2015, pp.3-1 to 3-8, ISBN 978-602-71964-5-2, published by Parahyangan Catholic University, Bandung, Indonesia

Parkash Surya, 2014: “A Selected Annotated Bibliography and Bibliography on Landslides in India” published by World Centre of Excellence on Landslide Disaster Reduction, National Institute of Disaster Management, Ministry of Home Affairs, Government of India, New Delhi, 2014, 172pages, ISBN: 978-93-85571-11-7, http://nidm.gov.in/PDF/pubs/bibliography%20landslide.pdf

Parkash Surya, 2012: “Training Module on Comprehensive Landslides Risk Management”, National Institute of Disaster Management, New Delhi, 2012, 282pages, ISBN: 978-81-924336-9-1, http://nidm.gov.in/PDF/modules/Landslide.pdf

Parkash Surya, 2012: “Capacity Development for Landslides Risk Reduction in India – A National Initiative for Loss Reduction”, Chapter-26, V-6, Part-V: Risk Management and Capacity Development,  Book: Landslides – Global Risk Preparedness by Kyoji Sassa, B. Rouhban and S. Briceno (Eds.), Springer-Verlag Berlin Heidelberg, 2012, pp.369-384, 978-3-642-22086-9 (Print) 978-3-642-22087-6 (Online)

Parkash Surya, 2011: “Historical Records of Socio-economically Significant Landslides in India”, Journal of South Asia Disaster Studies, published by SDMC – Delhi, Vol.4, No.2, December 2011, pp.177-204, ISSN 0974-6463

Note: Please fill and submit this form by 1 September 2018 to ICL Network <icl-network@iclhq.org> and ICL secretariat <secretariat@iclhq.org>